## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
| Today |  | 2024-11-13
| Project Team Name |  | Group 4 - BrumBytes
| Project Topic |  | Multi-Class Brain Tumour Detection Using MRI Images
| Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[9 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1. Title | Ideation |  |  | 2024-11-01 | 2024-11-02 | Brainstorm topics for capstone project |  | Done | bar: 2021-11-01 to 2021-11-13
| 1.1. Dataset Search |  |  | 2024-11-01 | 2024-11-02 | Search for reliable and existing datasets |  | Done | bar: 2021-11-01 to 2021-11-12
|  | 1.1.1. Exploratory Data Analysis |  | 2024-11-02 | 2024-11-02 | Compare and choose the best dataset | Final chosen dataset | Done | bar: 2021-11-01 to 2021-11-08
2. Data Preparation and Preprocessing |  |  |  | 2024-11-03 | 2024-11-05 |  |  | Done | bar: 2021-11-01 to 2021-11-06
| 2.1. Assess Quality of Input Data |  |  | 2024-11-03 | 2024-11-04 | Understand data distribution, identify missing values | Any identified missing values, and potential data quality issues | Done
| 2.2. Data Cleaning and Normalisation |  |  | 2024-11-03 | 2024-11-04 | Handle missing data, normalise image pixels | Cleaned and normalized MRI dataset | Done
| 2.3. Data Augmentation and Feature Engineering |  |  | 2024-11-04 | 2024-11-05 | Apply data augmentation techniques | Augmented dataset with increased variety of images | Done
3. Research and Model Selection |  |  |  | 2024-11-05 | 2024-11-06 |  |  | Done
| 3.1. Research Various Model Architectures |  |  | 2024-11-05 | 2024-11-05 | Assess strengths and weaknesses of models like CNN, ResNet, VGGNet | Research report outlining different potential model architectures, including strengths and weaknesses of each | Done
| 3.2. Select Baseline CNN Model |  |  | 2024-11-05 | 2024-11-05 | Choose a model for testing | Selected baseline CNN model architecture | Done
| 3.3. Establish Evaluation Metrics |  |  | 2024-11-05 | 2024-11-06 | Define evaluation metrics like accuracy, precision, recall, F1-score for model comparison and performance assessment | Defined evaluation metrics document (accuracy, precision, recall, F1-score) to be used in model assessment. | Done
4. Model Design and Setup |  |  |  | 2024-11-06 | 2024-11-07 |  |  | Done
| 4.1. Design CNN Architecture |  |  | 2024-11-06 | 2024-11-06 | Define the number of convolutional layers, pooling layers, and fully connected layers | Detailed architecture diagram and design document of the CNN model | Done
| 4.2. Image Preprocessing Techniques |  |  | 2024-11-06 | 2024-11-07 | Implement resizing, grayscale conversion, and filtering | Preprocessed images prepared for input into the CNN model | Done
| 4.3. Initial Hyperparameter Setup |  |  | 2024-11-07 | 2024-11-07 | Configure learning rate, batch size, and number of epochs for model training | Configuration file with initial hyperparameter settings | Done
5. Initial Training and Analysis |  |  |  | 2024-11-07 | 2024-11-09 |  |  | Done
| 5.1. Train Baseline CNN Model |  |  | 2024-11-07 | 2024-11-08 | To be done on the preprocessed MRI data | Trained baseline CNN model, along with initial training logs and loss/accuracy graphs | Done
| 5.2. Tumour Dimension Analysis |  |  | 2024-11-08 | 2024-11-08 | Research methods to analyse tumour size or volume and their impact on classification | Research findings on methods to analyze tumor size or volume, with a summary document explaining results | Done
| 5.3. Initial Model Evaluation |  |  | 2024-11-08 | 2024-11-09 | Evaluate model performance, identify areas for improvement in CNN model | Model evaluation report | Done
6. Model Optimisation and Hyperparameter Tuning |  |  |  | 2024-11-09 | 2024-11-10 |  |  | Done
| 6.1. Hyperparameter Tuning |  |  | 2024-11-09 | 2024-11-09 | Optimise learning rate, optimizer, batch size, epochs | Trained baseline CNN model, along with initial training logs and loss/accuracy graphs | Done
| 6.2. Model Refinement |  |  | 2024-11-09 | 2024-11-10 | Adjust number of layers, dropout rates, and regularisation techniques to reduce overfitting | Optimized hyperparameter configuration file | Done
7. Model Deployment |  |  |  | 2024-11-10 | 2024-11-11 |  |  | Done
| 7.1. Setup Flask Framework |  |  | 2024-11-10 | 2024-11-10 | Setup flask framework for model deployment | Flask application structure with the necessary configuration files for model deployment | Done
| 7.2. Deploy CNN Model |  |  | 2024-11-11 | 2024-11-11 | Deploy CNN model onto Flask server, integrate it to web interface |  | Done
8. Explainability and Interpretation |  |  |  | 2024-11-11 | 2024-11-12 |  |  | Done
| 8.1. Implement Explainable AI |  |  | 2024-11-11 | 2024-11-11 | Integrate LIME for explainability for visual insights into model decision making | Integrated LIME libraries into the deployed model | Done
| 8.2. Explainability Testing |  |  | 2024-11-12 | 2024-11-12 | Test and ensure the explainability visualizations are clear | Explainability test results, ensuring clarity of LIME output | Done
9. Final Evaluation, Documentation and Presentation |  |  |  | 2024-11-12 | 2024-11-13 |  |  | Done
| 9.1. Final Model Evaluation |  |  | 2024-11-12 | 2024-11-13 | Evaluate final CNN model on validation and test sets using defined metrics | Model evaluation report, including performance on validation and test sets using all metrics | Done
| 9.2. Final Documentation |  |  | 2024-11-13 | 2024-11-13 | Prepare final project report with evaluation results | Complete project documentation, including all technical details, model design, evaluation results, preprocessing steps, and images | Done
| 9.3. Presentation Preparation |  |  | 2024-11-13 | 2024-11-13 | Prepare slides, add images and a draft script | Final presentation slides, including key findings, model insights, visualizations, and explainability aspects | Done
This date is illustration
These status are illustrations